## Backlog
Story Title | Description | Acceptance Criteria | Priority | MVP? | Points | Sprint
Finalize Test Workbook Data Model & Design | Finalize the data model, design and format of the Test Workbook so that downstream stories that are impacted by the Workbook can proceed | Test Workbook design stable and approved by team | 1-High | Y
Workbook Generator | Create a program to generate an empty Test Workbook. | Ability to generate an empty Test Workbook from a command-line | 3-Low | N
Workbook Validator | Create a program to validate the data entered in a Test Workbook is correct before running the tests. Checks can be either Warnings or Errors. Some examples of checks are: TBD | Ability to validate Test Worbook data before running tests. Less serious issues will be displayed as Warnings, and the tests will still run. More serious issues will be displayed as Errors and the tests will not continue. | 2-Med | Y
Workbook to Text Converter | Create a program that will take the Excel Test Workbook and convert it into an intermediary format (xml or json) that can be stored as plain text, and edited without having to use Excel. This can then been used by the Test Runner and other sub programs. | Command-line program that converts Test Workbook to text (xml or json) format. | 2-Med
Test Runner | Create a Test Runner program that is the main command-line interface for running DataUnit. The Test Runner should be called "dataunit" (or something similar) and should accept as a parameter the Test Workbook. Optionally the converted Test Workbook in xml or json format can be passed. The Test Runner then takes the Tests in the Test Workbook and converts them to executable tests and then runs them. Initially this can be as simple as converting the tests to Python unittest tests, and then running them. Finally, the Test Runner should display the test results back to the user. | Working test runner with ability to pass a Test Workbook from the command-line and get back test results. | 1-High | Y
Test Command: Execute SQL | Test command that will accept a SQL Command, along with Database Connection information as parameters, and then execute that command, and capture whether or not the command was successful. | Working test command that can execute a SQL statement against SQL Server via ODBC, and reports back success or failure | 1-High | Y
Test Command: Execute SQL with Dataset | Test command that will accept a SQL Command that produces a dataset (Select, etc), along with Database Connection information as parameters, and then execute that command, and capture the results, along with whether or not the command was successful. | Working test command that can execute a SQL statement that produces a dataset against SQL Server via ODBC, and returns the dataset along with success or failure. | 1-High | Y
Test Command: Load Dataset to Table | Test command that will accept a dataset from one of the sheets in the Test Workbook, and load it to a SQL Table. The dataset will be provided to the command as a parameter, along with the database connection information, and the target table. | Working test command that can take a dataset from the Test Workbook, and load it via ODBC to a SQL table, and returns a success or failure. | 1-High | Y
Test Command: Assert Datasets Equal | Test command that accepts two datasets and compares them for equality. If equal then the assertion passes, if not equal the assertion fails. This would be used to then fail tests that need to compare two datasets. | Working assertion test command that can take two datasets as parameters and raises a failure if they are not equal. | 1-High | Y
Test Command: Assert Record Count Equal | Test command that compares the expected and actual record counts of a SQL statement and asserts that they are equal | Working assertion test command that takes an expected record count and compares it to the actual record count of a dataset or SQL statement and raises a failure if they are not equal | 1-High | Y