## dataunit-dataunit_issues_2020-0
Issue ID | Title | State | Description | Confidential | Locked | Due Date | Created At (UTC) | Updated At (UTC) | Closed At (UTC) | Milestone | Weight | Labels | Time Estimate | Time Spent
3 | Workbook Generator | Open | Create a program to generate an empty Test Workbook. AC: Ability to generate an empty Test Workbook from a command-line | No | No |  | 2018-02-04 03:41 | 2018-02-04 03:41 |  |  |  | Low | 0 | 0
4 | Workbook Validator | In Progress | Create a program to validate the data entered in a Test Workbook is correct before running the tests. Checks can be either Warnings or Errors. Examples: Error - Missing required worksheet Warning - Test without Test Commands AC: Ability to validate Test Workbook data before running tests. Less serious issues will be displayed as Warnings, and the tests will still run. More serious issues will be displayed as Errors and the tests will not continue. | No | No |  | 2018-02-04 03:47 | 2018-02-04 03:47 |  | Release 1.0 |  | Med | 0 | 0
5 | Workbook to Text Converter | Open | Create a program that will take the Excel Test Workbook and convert it into an intermediary format (xml or json) that can be stored as plain text, and edited without having to use Excel. This can then been used by the Test Runner and other sub programs. AC: Command-line program that converts Test Workbook to text (xml or json) format. | No | No |  | 2018-02-04 03:49 | 2018-02-04 03:49 |  |  |  | Low | 0 | 0
6 | Test Runner | In Progress | Create a Test Runner program that is the main command-line interface for running DataUnit. The Test Runner should be called "dataunit" (or something similar) and should accept as a parameter the Test Workbook. Optionally the converted Test Workbook in xml or json format can be passed. The Test Runner then takes the Tests in the Test Workbook and converts them to executable tests and then runs them. Initially this can be as simple as converting the tests to Python unittest tests, and then running them. Finally, the Test Runner should display the test results back to the user. AC: Working test runner with ability to pass a Test Workbook from the command-line and get back test results. | No | No |  | 2018-02-04 03:50 | 2018-03-03 01:49 |  | Release 1.0 |  | High | 0 | 0
7 | Test Command: Execute SQL | Closed | Test command that will accept a SQL Command, along with Database Connection information as parameters, and then execute that command, and capture whether or not the command was successful. AC: Working test command that can execute a SQL statement against SQL Server via ODBC, and reports back success or failure | No | No |  | 2018-02-04 03:51 | 2018-02-04 03:52 | 2018-02-04 03:51 | Release 1.0 |  | High | 0 | 0
8 | Test Command: Execute SQL with Resultset | Open | Test command that will accept a SQL Command that produces a resultset (Select, etc), along with Database Connection information as parameters, and then execute that command, and capture the results, along with whether or not the command was successful. AC: Working test command that can execute a SQL statement that produces a dataset against SQL Server via ODBC, and returns the dataset along with success or failure. | No | No |  | 2018-02-04 03:53 | 2018-02-04 03:53 |  | Release 1.0 |  | High | 0 | 0
9 | Test Command: Load Dataset to Table | Closed | Test command that will accept a dataset from one of the sheets in the Test Workbook, and load it to a SQL Table. The dataset will be provided to the command as a parameter, along with the database connection information, and the target table. AC: Working test command that can take a dataset from the Test Workbook, and load it via ODBC to a SQL table, and returns a success or failure. | No | No |  | 2018-02-04 03:54 | 2018-02-04 03:54 |  | Release 1.0 |  | High | 0 | 0
10 | Test Command: Assert Datasets Equal | Open | Test command that accepts two datasets and compares them for equality. If equal then the assertion passes, if not equal the assertion fails. This would be used to then fail tests that need to compare two datasets. AC: Working assertion test command that can take two datasets as parameters and raises a failure if they are not equal. | No | No |  | 2018-02-04 03:56 | 2018-02-04 03:56 |  | Release 1.0 |  | High | 0 | 0
11 | Test Command: Assert Record Count Equal | Open | Test command that compares the expected and actual record counts of a SQL statement and asserts that they are equal AC: Working assertion test command that takes an expected record count and compares it to the actual record count of a dataset or SQL statement and raises a failure if they are not equal | No | No |  | 2018-02-04 03:56 | 2018-02-04 03:56 |  | Release 1.0 |  | High | 0 | 0
12 | Test Case Management | Closed | As an ETL Tester I need to write and maintain test cases so that I can easily manage and edit automated test suites. Acceptance Criteria: * I can enter and maintain test case definitions. * I can manage test suites and cases using a single tool or interface. * I can enter and update all metadata necessary to define test cases. Tasks: * [x] Decide between declarative and imperative approach to test case development * [x] Decide what the user interface will be (excel vs something else) * [x] Identify all necessary metadata * [x] Build the UI Metadata ============== Tests Worksheet -------------- * Test Name - Unique identifier for a test (required) * Active - Indicates if the test is to be run (Y/N) (required, default to Active = Y if left blank) * Test Description - Description of the test (optional) * Test Commands Worksheet - The name of the worksheet that contains the test commands Test Commands Worksheet (name of worksheet defined on the Tests worksheet) --------------- * Active - Indicates if the test command is to be run (Y/N) * Command Description - Description of the test command (optional) * Command - the test command to run * Parameter N Name (N = minimum needed for our commands) * Parameter N Value Variables -------------- * Test Case Scope, Mutable between test commands, but not test cases * should be declared as a test command * not MVP unless needed for something else that is MVP Settings -------------- * Constants that can be used as built-in settings to control DataUnit * can also constants to be used for tests (i.e. Connection Info, etc) * Built-in settings are not displayed initially but can be overriden in the Settings sheet, and defaulted in the DataUnit runner Drop-downs -------------- Not MVP, but nice to have if we can figure a way to do it in a maintainable and generated format May have trouble when we upgrade to a new version to add new commands | No | No |  | 2018-03-02 18:01 | 2018-03-30 13:57 |  | Release 1.0 |  | MVP,Story,To Do | 0 | 0
13 | Test Execution | Closed | As an ETL tester, I need to execute test cases that I've defined and see the results so I can ensure my ETL processes are functioning properly. Acceptance Criteria: * I can execute all defined test cases * I can run tests from command-line (to facilitate non interactive/headless execution) * I can see results of all test cases (Number of tests that Passed, Failed, Errored) Nice to have: * Ability to output test results in standard junit xml formatting so that it can be consumed by other tools such as jenkins, tfs, etc Tasks * [x] Context Management | No | No |  | 2018-03-03 01:08 | 2018-05-11 20:13 |  | Release 1.0 |  | Doing,MVP,Story | 0 | 0
15 | Manage Test Data | Closed | As an ETL tester, I need to manage my test data sets in a tabular way so that I can easily develop and maintain data sets to exercise all scenarios in my ETL processes. Acceptance Criteria: * I can enter and manage tabular data sets in a grid format * I can edit/copy/paste individual data cells, as well as entire records of data * I can uniquely identify a test data set so that I can associate it with a test definition * I can reuse test data sets across multiple test definitions Design -------------------- * One sheet per dataset * Column Header is in the first row * The name of the sheet is the dataset identifier | No | No |  | 2018-03-03 01:15 | 2018-03-30 14:11 |  | Release 1.0 |  | MVP,Story,To Do | 0 | 0
16 | Test SQL Server Views | Open | As an ETL Tester, I need to be able to test my MS SQL Server views so that I can ensure they perform the correct transformations. Acceptance Criteria: * Using DataUnit I can test a SQL Server view * I can run test in a transaction that can be rolled back at the end so that my database is not affected * I can specify one or more test data sets to be used as source data for the view * I can specify a test data set as the expected output * The system should be able to compare the actual view output and the expected output and capture and report differences (i.e. test fails if data sets don't match) | No | No |  | 2018-03-03 01:20 | 2018-03-08 18:00 |  | Release 1.0 |  | MVP,Story,To Do | 0 | 0
17 | Test SQL Server Stored Procedures | Open | As an ETL tester, I need to be able to test my SQL Server Stored Procedures so that I can ensure that they perform the correct processing. Acceptance Criteria: * Using DataUnit I can test a SQL Server procedure * I can run test in a transaction that can be rolled back at the end so that my database is not affected * I can specify input parameters with their values * I can specify one or more test data sets to be used as source data for the stored procedure * I can specify zero, one or more test data set as the expected output * The system should be able to compare the actual stored proc output and the expected output and capture and report differences (i.e. test fails if data sets don't match) Assumption: * Stored proc output can include return values, output parameters, result sets that are selected by a select statement within the proc, or external tables | No | No |  | 2018-03-03 01:29 | 2018-03-08 17:59 |  | Release 1.0 |  | MVP,Story,To Do | 0 | 0
18 |  | Open | Set up new GitHub repository * Changing from user to organization * Transfer code from bigdatamoore to dataunit * Grant Mike access to new repo * Set up project board | [11 empty] | David
19 | Containerize SQL Server | Open | Containerize database used to test dataunit (SQL Server) * Use Docker * Dockerfile that pulls down the image you want to run as a container Acceptance Criteria: 1. Docker image and container that installs and runs MyFitBot SQL Server database 2. Tests are able to connect to the database on running container | [8 empty] | High |  |  | David/Mike
20 |  | Open | Make sure dataunit functions with Execute Shell Command Acceptance Criteria: 1. dataunit can execute a "hello, world" Shell Command | [11 empty] | Mike